## Sheet1
3902 Sprint 4 Initial Planning
Backlog | Task | Information | Prerequisits | Due Date | Effort | Team Member
Level Loading | Level Class | Needs to load the entire world |  |  | 10 | Oliver
|  | Needs additional game objects at the beginning of the level to allow for easy testing |  |  | 0
|  | Needs to be able to add, remove, and replace any object from the list it is in with an object of the same type |  |  | 2
| xml File | Needs to be able to differentiate between a PowerUpQuestionBlock and a CoinQuestionBlock for instance |  |  | 6
Update the xml to have all of the data to load the entire world plus the testing at the beginning
Player | Rename Player class to Mario |  |  | 2014-06-18 | 1 | Derek
| Add a player interface, Iplayer |  |  | 2014-06-18 | 1
| Allow Fire mario to shoot fireballs |  |  |  | 3
| Correct mario transitions |  |  |  | 1
| Make star mario a decorator pattern |  | Level |  | 2
| Add lives counter to mario |  | Level |  | 1
| Change from implimenting IGameObject to extending abstract gameobject |  | abstract gameobject | 2019-06-18 | 1
| Abstract mario class and possible separation of mario states into classes |  |  |  | 3
| Jumping | Should only jump when it in on the ground | Level and collision |  | 2
Collision | UpdateCollisionHandler | call the appropriate response(s) | Responses and level |  | 6
| MoveToResponse | Tells the game object to move to the given position | All game objects positions can be moved. This may need broken down into separate responses.
| BumpBlockResponse | Tells the given block to bump | Blocks have public bump method |  | 1
| BreakBlockResponse | Break the given brick block | Brick block has a break method |  | 1
| BecomeVisibleResponse | Make the given invisible block visible | Invisible block has a BeVisibleMethod |  | 1
| DamageMarioResponse | Tell mario to take damage | Mario has a take damage method |  | 1
| BecomeFireMarioResponse | Tell mario to become fire mario | Mario has a BecomeFire method |  | 1
| BecomeStarMarioResponse | Tell mario to become star mario | Mario has a BecomeStar method |  | 1
| BecomeBigMarioResponse | Tell mario to become big mario | Mario has a BecomeBig method |  | 1
| ChangeEnemyDirectionResponse | Tell the given enemy to change directions | Enemies have a change direction method |  | 1
| SmashEnemyResponse | Tell the enemy to be smashed | Enemies need a BeSmashed method |  | 1
| DamageEnemyResponse | Tell the enemy to take damage | Enemies need a TakeDamage method |  | 1
Enemies | Movement | Enemies need to move when the update method is called |  |  | 1 | Stella
|  | Keep track of the direction it is heading. Probably just a boolean variable |  |  | 1
|  | Add a method to change the enemies direction |  |  | 1
| Change from implimenting IGameObject to extending abstract gameobject |  | abstract gameobject | 2019-06-18 | 1
| Abstract class | Create an abstract enemy class which impliments IEnemy and then every enemy extends that abstract class |  |  | 2
Blocks | Add Bump method to block interface |  |  |  | 1 | Levi
| Add IsBumped method to block interface |  |  |  | 1
| Create an abstract block class | Create an abstract block class which impliments Iblock and then every block extends that abstract class. This should be done early as it will make the others easier. |  |  | 2
| Impliment Bump method | This can be done as either a state machine, state pattern, or decorator pattern |  |  | 2
| Separate QuestionBlock into multiple classes | The question block becomes a PowerUpQuestionBlock, CoinQuestionBlock. |  |  | 3
| Separate InvisibleBlock into multiple classes | The InvisibleBlock becomes NormalInvisibleBlock, PowerUpInvisibleBlock |  |  | 3
| Separate BrickBlock into multiple classes | The BrickBlock becomes NormalBrickBlock, StarBrickBlock, CoinBrickBlock. |  |  | 3
| Change from implimenting IGameObject to extending abstract gameobject |  | abstract gameobject | 2019-06-18 | 1
| Update Update method | Allow update to move the block if it is being bumped | Physics class |  | 1
Fireball | Move fireball on update |  | Physics class and abstract gameobject |  | 1 | Stella
| Change from implimenting IGameObject to extending abstract gameobject |  |  | 2019-06-18 | 1
| Constructor will take a velocity |  |  |  | 1
Camera | Implement a Camera |  |  |  | 10
| Add a Camera interface | GetPosition() |  |  | 1
SetPosition(Vector2)
Others?
ResetLevel | Reset the level upon all players being dead | No Idea. Will need to ask or get more information |  |  | 10
Items | Move items | Some items move around. The star bounces, the mushrooms slide. Physics plays an effect on them. | Physics class |  | 4 | Oliver
| ICollectable | Collect() |  |  | 1
| Change from implimenting IGameObject to extending abstract gameobject |  | abstract gameobject | 2019-06-18 | 1
| Coin separated into separate classes | The coin becomes SpawnedCoin StaticCoin. SpawnedCoin is a gameObject but is not collidable or collectible. StaticCoin is a gameobject and is collidable and collectible. |  |  | 3
GameObject | Abstract CollidableGameObject class | Impliments IGameObject and Icollidable. Other classes which currently impliment IGameObject and ICollidable should be changed to extend this abstract class instead. |  | 2019-06-16 | 1 | Derek
Physics | Physics class | Contains position, velocity, and acceleration in the x and y direction and a boolean for applying friction. Contains an update method which calculates the new velocity and position. |  | 2019-06-16 | 1 | Derek
Separate Interfaces | Create IUpdatable |  |  | 2019-06-18 | 1 | Derek
Create IDrawable
Update Isprite and IGameObject to use Iupdatable and Idrawable
Planning | Plan for Sprint 4 | Preliminary planning and task creation and definition |  | 2019-06-14 | 8 | Derek