## Sheet1
Backlog | Task | Information | Prerequisits. (Doesn't mean it can't be started, just that it can't be finished) | Date Due | Assigned to
Heads up display |  | Should be singleton. Display lives left for first mario. Display level title. Ask the game manager for milliseconds left. | Game manager, ScoreBoard | 2019-07-05
GameManager | Pause(), Unpause(), IsPaused(), ResetLevel(), ResetGame(), Update(), (All of the methods LevelManager currently has), GetScore(), AddScore(ScoreTag) | Should be singleton. Takes care of the game timer. Updates all of the game objects. Takes care of Level transitions. Holds a stack of levels for underground. Holds a dictionary of levels(<(NameOfCurrentLevel,"Underground"/"NextLevel"),NameOfAssociatedLevel>). Could load this in from a Levels.xml file. Takes care of players so the level can be reset without making new players and reseting life counts. Adds points based on time when level is complete. | LevelManager, ScoreBoard | 2019-07-09 | Derek
Controller | PauseCommand, UnpauseCommand, ResetGameCommand |  | GameManager | 2019-07-09 | Derek
LevelManager | Take away singleton so the level manager can hold more than one level at the same time. No longer takes care of players. |  |  | 2019-07-09 | Derek
Mario | DeadMario |  |  | 2019-07-04 | Derek
SoundManager | PlayBackgroundMusic(SoundTag), StopBackgroundMusic(), PlaySound(SoundTag), SoundTag enum, SoundDictionary, Sound files, Sounds.xml | Should be singleton. SoundTag enum. Load sounds from Sounds.xml. PlayBackgroundMusic() keeps the tag given and loops it when it ends. Probably other things are needed and will need to be researched. |  | 2019-07-05
ScoreBoard | GetScore(), AddPoints(int) |  |  | 2019-07-04 | Oliver
Despawn Objects |  |  |  | 2019-07-05
Remove Magic Numbers and Strings |  |  |  | 2019-07-10
Underground level |  |  |  | 2019-07-07 | Oliver